## Sheet1
Title (short, descriptive name of project) | Objective (the desired outcome of the project) | High Level Strategy (alignment with other, higher level efforts at King County) | Key Measure (how success is measured) | Reason (why it is relevant) | Key Measure Goal (what the goal is for; expectation of key measure) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached) | Milestone (description of occurrence or future marker) | Date (when the marker will be reached)
2026 Draft - Best Run Government Progression | In 2025, OEM scored a "3" in 6/11 of the categories of the BRG Roadmap Assessment, and a "4" in 5/11 categories. In 2026, OEM aims to maintain these scores and increase the number of "4" scores to six (6). | Alignment with and furtherance of Better Government | 3 in all categories and at least six (6) "4" scores | Signifies advancement of the concept of Best Run Government. | Total score of 36 or greater. | Implement, continue, and monitor employee engagement plan activities. | 2026-04-30 | Distribute updated (as necessary) survey to all staff members to gather information about BRG Roadmap Assessment, analyze collected survey information, and report out to staff and DES leadership on results of BRG Roadmap Assessment Survey. | 2026-09-30 | Continue "Voice of the Customer” measurement/methodology for unincorporated areas and regional emergency managers. | Quarterly | Regular meetings with: regional (King County) emergency management directors; EMD Director; Pierce, Thurston, and Snohomish County emergency management directors and public health preparedness leads; PHSKC Public Health Preparedness Director; and, others as appropriate. | Monthly | Employee engagement events at Rounding and other forums (e.g., Firehouse Lunch, Disaster Movie Series, etc.) throughout the year. | Monthly
2026 Draft - Public Information | OEM facilitates Public Information and Warning so that government agencies, and public, and private sectors, receive and transmit coordinated, prompt, useful, and reliable information regarding threats to their health, safety, and property, through clear and consistent information delivery systems. This information is updated regularly and outlines protective measures recommended for individuals and their communities. | Alignment with and furtherance of the Comprehensive Emergency Management Plan (CEMP) and assocated plans. | Increase in public engagement | Demonstrates commitment to OEM mission and vision | Overall 8% increase in engagement | Increase number of people engaged with the public education program which includes: outreach events, social media content, and the long term development of curriculum and outreach materials. | Quarterly | Increase the Trusted Partner Network marketing and outreach, focusing on language gaps identified in Inclusive Emergency Communications Plan; increase usage of TPN by partner jurisdictions; coordinate efforts with ALERT King County marketing to LEP communities. | 2026-12-31 | Deepen bench of trained PIO partners by 50%; Review, update, train, and exercise on the new JIC/JIS Guide with appropriate county and city PIO partners. Train partner PIOs to staff the WA WC26 JIC. | 2026-03-31 | Increase ALERT King County subscriptions by 4% (of current subscriptions). Increase public engagement: Develop and implement strategies for increasing registrations for ALERT King County. | 2026-12-31
2026 Draft - Regional Integration | OEM enhances governmental and community preparedness and participation by facilitating structured collaboration between government and non-governmental resources into plans and exercises, and providing resources to support communities. Through public education initiatives that train residents and specialized professional training for emergency responders, the program strengthens community resilience and includes a process for evaluating progress in emergency management efforts. | Alignment with and furtherance of the Comprehensive Emergency Management Plan (CEMP) and assocated plans. | Increase in attendance at meetings | Increased attendance can be equated to increased cooperation, collaboration, and communication. | Overall 8% increase in attendance. | Evaluate the bleeding control program objectives and deliverables to identify gaps from previous grant funding rounds and establish a robust County Stop-the-Bleed training programme. | 2026-09-30 | Strengthen regional coordination and situational awareness by maintaining quarterly contact with King County jurisdictions, documenting emerging needs and trends, and facilitating resource connections to improve communication, support, and preparedness across all city and district partners. | Quarterly | Ensure ongoing policy and operational coordination among regional and county stakeholders in EMAC and EMCC meetings each while producing quarterly reports summarizing participation, key decisions, and future priorities for OEM work-product. | Quarterly | Develop partnerships within the King County business community to enhance connectivity before disasters and continuity following a disaster. | Biannually | Update and verify Community Point of Distribution (CPOD) sites in unincorporated King County (verify 2019 RCPGP CPOD information). | 2026-05-31 | Manage a robust Local Emergency Planning Committee (LEPC) Program, one that maintains and updates the HazMat Plan, and has representatives from all required entities (public and private). OEM exceeds expectations hosting 4 LEPC meeting a year. | Quarterly | Increase partner readiness and professional capacity by delivering pertinent training offerings, achieving steady or increased annual participation, and ensuring all training aligns with regional priorities and King County’s Best Run Government commitments. | Monthly | Enhance operational readiness through the completion of the annual THIRA/SPR assessment, coordination of staff or partner exercises, and implementation of the Improvement Plan to address identified capability gaps. Conduct quarterly drills and evaluations to ensure continuous improvement in preparedness and response performance. | 2026-12-31
2026 Draft - Operations | OEM facilitates response preparedness and operations so that events and incidents are effectively managed through multi-agency coordination whether pre-planned or no-notice. Across all activation levels, ensure critical resources are available upon request for proper distribution in a cost-effective and timely manner. Additionally, support effective and timely sharing of information and intelligence occurs across King County regional partners, to achieve coordinated awareness of, prevention of, and response to threatened or actual event. During activations, oversee EOC management to include activating and operating the KC EOC for pre-planned and no-notice events. | Alignment with and furtherance of the Comprehensive Emergency Management Plan (CEMP) and assocated plans. | Equipment, technology, and other resources are maintained in operational condition. | Supports execution of statutory roles and responsibilities of OEM. | Existing resources are available 100% of the time, and new resources are implemented within established time frames. | Establish deployable asset packages and determine communication avenue for regional partners. | 2026-03-31 | Manage robust duty officer program to sustain trained duty officers able to respond 24/7. | Monthly | Procure and prepare for deployment one deployable cell site with AT&T and Verizon capability. | 2026-06-30 | Transition from WebEOC 9 to Nexus. | 2026-09-30 | Complete alert and warning system RFP process and, if necessary, transition to new system. | 2026-10-31
2026 Draft - Financial Management | Economic resource needs are estimated; priorities are set for funding activities; financial assistance is sought through grants for preparedness and operation activities; and when available, recovery assistance is provided to eligible recipients with minimal delay. | Alignment with and furtherance of the Comprehensive Emergency Management Plan (CEMP) and assocated plans | Funds are expended consistent with forecasted timelines and financial reports are accurate and submitted on time. | Timely spending ensures that program delivery stays on track, which supports compliance and decision making, and protects against audit risk. | At least 90% of funds are expended in alignment with forecasts, and 100% of required financial reports are submitted by deadlines with no material errors. | Completed annual financial audit preparation and participation. | 2026-07-31 | Finalized grant agreements; confirmed budget allocations; kickoff meetings with program/project managers to align expectations and timelines. | Monthly | Completed SEFA and SESFA submissions to FBOD by established deadlines. | 2026-04-15 | Monthly billings submitted to grantors. | Monthly | Quarterly grant reports completed and submitted to grantors. | Quarterly
2026 Draft - Planning | OEM facilitates planning so that plans incorporate an accurate threat analysis and risk assessment and ensure that capabilities required to mitigate, prevent, protect against, respond to, and recover from all-hazards events are available when and where they are needed. Plans are vertically and horizontally integrated with appropriate departments, agencies, and jurisdictions. Where appropriate, Emergency plans incorporate a mechanism for requesting state and federal assistance, and include a clearly delineated process for seeking and requesting assistance from appropriate partners. | Alignment with and furtherance of the Comprehensive Emergency Management Plan (CEMP) and assocated plans. | Progression through the Preparedness Cycle | Training is provided on all completed mission area plans. | Development of plans must be followed by implementation, training, validation, assessment, and revision. | Stakeholder agreement on key components/products of King County Fuel Plan project and timeline for next steps. | 2026-06-30 | Training on the CEMP is delivered to 100% of partners and a training video is developed. | 2026-12-31 | Complete internal and external partner workshops for the Recovery Mission Area Plan. | 2026-05-31 | Develop, with planning partners, the capability annexes to the Prevention/Protection Mission Area Plan. | 2026-12-31 | Mature the Recovery Support Function Annexes to the Recovery Mission Area Plan. | 2026-10-31 | Develop a coordinated countywide Damage Assessment Plan. | 2026-10-31 | Continued development, socialization and training of the Prevention/Protection Mission Area Plan with internal and external partners. | 2026-09-30 | Track mitigation strategies by annexes and facilitate working groups by strategy themes to enabling participants to share resources, exchange best practices, learn from one another’s experiences, and better understand the capabilities and assets available across jurisdictions. | Quarterly | Maintain a working hazard mitigation committee of county agencies that does bi annual updates on current mitigation work done throughout the county. Create a spreadsheet of all mitigation work being done in the county and who is responsible for the work. Ensure Regional Hazard Mitigation Plan (RHMP) also meets Emergency Management Accreditation Program (EMAP) approval. | 2026-12-31 | Fulfill the requirements of King County Code (KCC 2.56.040) that states each executive level branch department must have a Continuity of Operations plan and fulfill Emergency Management Accreditation Program (EMAP) continuity requirements for EMAP assessment. | 2026-12-31 | Support progress and implementation of Community Wildfire Protection Plan (CWPP) mitigation strategies, including leading KCOEM specific actions and supporting partner projects outlined in CWPP. | 2026-05-31 | By the end of 2026, collaboratively develop a final draft of a basin-specific response plan through active partner engagement and coordinated planning. | 2026-12-31 | acilitate Planning processes for operational plans and documents to include: Job Aids, Duty Officer procedures, and Playbooks. Ensure annually updated plans. | 2026-12-31